## Sheet1
| 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01
Validate Frame Data in Queue | bar: 2026-01-23 to 2026-01-30
Integrate app with Firestore backend | bar: 2026-01-30
Redesign power supply | bar: 2026-01-16 to 2026-01-30; 2026-03-13
Status Update Presentation #1 | 2026-03-20: Not Started
Complete and order new PCB and parts | bar: 2026-01-30 to 2026-02-06; 2026-03-13
Connect Raspberry Pi with Cloud Firestore | 2026-03-20: In Progress
Migrate ML Model to Pi | 2026-03-20: Completed
Get ML to read in data from pi | 2026-03-20: Late
FBase Cloud Functions for alert notifications | bar: 2026-01-30 to 2026-02-06
Status Update Presentation #2 | bar: 2026-02-13
Solder and validate completed power supply | bar: 2026-02-20 to 2026-03-06
Synchronize data collection in MCU | bar: 2026-02-20 to 2026-02-27
End-to-end alert validation (Pi ,Cloud ,App) | bar: 2026-02-20 to 2026-03-06
Status Update Presentation #3 | bar: 2026-02-27
Integrate power supply and Final Integration | bar: 2026-02-27 to 2026-03-06
App acknowledgment and latency validation | bar: 2026-03-06 to 2026-03-13
Verify correct data pipeline in MCU | bar: 2026-03-13 to 2026-03-20
Status Update Presentation #4 | bar: 2026-03-20
Overall validation & performance test | bar: 2026-03-27 to 2026-04-03
Status Update Presentation #5 | bar: 2026-04-03
Design radome | bar: 2026-04-03
Construct radome | bar: 2026-04-10
Full System Test | bar: 2026-04-10
Final testing and validation | bar: 2026-04-17
Project documentation | bar: 2026-04-17
Final Presentation | bar: 2026-04-17
Demo | bar: 2026-04-24
Final Report | bar: 2026-05-01